## Gantt Chart & Burndown
CPE178P – Smart Waste Image Classification and Monitoring System
Project Schedule / Gantt Chart – Lester Van E. Rivera (Solo Project)
Schedule aligned with the currently visible Blackboard deadlines: Project Proposal – Oct. 4, Sprint 1 – Oct. 7, Sprint 2 – Oct. 11, Final Project – Oct. 11, 2026.
WBS | Task Title | Task Owner | Estimate (hrs) | Complete (hrs) | Remaining (hrs) | Sprint | Start Date | Due Date | Duration (days) | % Complete | Status | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
1.0 | Project Proposal and Project Setup | Rivera, L. | 12 | 6 | 6 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 50% | In Progress | ■ | ■ | ■ | ■
1.1 | Finalize Project Proposal | Rivera, L. | 6 | 6 | 0 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 100% | Complete | ■ | ■ | ■ | ■
1.2 | Set Up Development Environment and Dependencies | Rivera, L. | 2 | 0 | 2 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 0% | Not Started | ■ | ■ | ■ | ■
1.3 | Create GitHub Repository and Initial Commit | Rivera, L. | 2 | 0 | 2 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 0% | Not Started | ■ | ■ | ■ | ■
1.4 | Prepare Sprint 1 Evidence and Documentation | Rivera, L. | 2 | 0 | 2 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 0% | Not Started | ■ | ■ | ■ | ■
2.0 | Dataset Preparation and Baseline Deep Learning Model | Rivera, L. | 24 | 0 | 24 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 0% | Not Started | ■ | ■ | ■ | ■
2.1 | Acquire and Inspect TrashNet Dataset | Rivera, L. | 4 | 0 | 4 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 0% | Not Started | ■ | ■ | ■ | ■
2.2 | Clean, Preprocess, and Split Dataset | Rivera, L. | 5 | 0 | 5 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 0% | Not Started | ■ | ■ | ■ | ■
2.3 | Implement Baseline CNN | Rivera, L. | 6 | 0 | 6 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 0% | Not Started | ■ | ■ | ■ | ■
2.4 | Train and Evaluate Baseline Model | Rivera, L. | 6 | 0 | 6 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 0% | Not Started | ■ | ■ | ■ | ■
2.5 | Record Sprint 1 Development Evidence | Rivera, L. | 3 | 0 | 3 | Sprint 1 | 2026-10-04 | 2026-10-07 | 4 | 0% | Not Started | ■ | ■ | ■ | ■
3.0 | Project Sprint 2 and Final System Integration | Rivera, L. | 38 | 0 | 38 | Sprint 2 | 2026-10-08 | 2026-10-11 | 4 | 0% | Not Started |  |  |  |  | ■ | ■ | ■ | ■
3.1 | Refine/Finalize Deep Learning Model | Rivera, L. | 6 | 0 | 6 | Sprint 2 | 2026-10-08 | 2026-10-11 | 4 | 0% | Not Started |  |  |  |  | ■ | ■ | ■ | ■
3.2 | Integrate FastAPI Backend | Rivera, L. | 7 | 0 | 7 | Sprint 2 | 2026-10-08 | 2026-10-11 | 4 | 0% | Not Started |  |  |  |  | ■ | ■ | ■ | ■
3.3 | Integrate Flet Graphical Interface | Rivera, L. | 7 | 0 | 7 | Sprint 2 | 2026-10-08 | 2026-10-11 | 4 | 0% | Not Started |  |  |  |  | ■ | ■ | ■ | ■
3.4 | Integrate Image Input and Classification Workflow | Rivera, L. | 5 | 0 | 5 | Sprint 2 | 2026-10-08 | 2026-10-11 | 4 | 0% | Not Started |  |  |  |  | ■ | ■ | ■ | ■
3.5 | ONNX Export/Runtime Verification | Rivera, L. | 4 | 0 | 4 | Sprint 2 | 2026-10-08 | 2026-10-11 | 4 | 0% | Not Started |  |  |  |  | ■ | ■ | ■ | ■
3.6 | System Testing and Debugging | Rivera, L. | 5 | 0 | 5 | Sprint 2 | 2026-10-08 | 2026-10-11 | 4 | 0% | Not Started |  |  |  |  | ■ | ■ | ■ | ■
3.7 | Final Documentation, README, and Demonstration Preparation | Rivera, L. | 4 | 0 | 4 | Sprint 2 | 2026-10-08 | 2026-10-11 | 4 | 0% | Not Started |  |  |  |  | ■ | ■ | ■ | ■
Key Submission Milestones
Project Proposal | 10/04/2026 | Proposal PDF / required schedule
Project Sprint 1 – Individual Submission | 10/07/2026 | Individual Sprint 1 evidence and contribution
Project Sprint 1 – Group Deliverables | 10/07/2026 | Group deliverables; solo project still follows required artifacts
Project Sprint 2 – Individual Submission | 10/11/2026 | Sprint 2 individual submission
Project Sprint 2 – Group Deliverables | 10/11/2026 | Sprint 2 group deliverables
Final Project Deliverables | 10/11/2026 | Presentation video, documentation, source code + README

## Burndown
Project Burndown
Planned remaining work across the Oct. 4–11 project window.
Date | Planned Remaining Hours | Actual Remaining Hours | Milestone
2026-10-04 | 130 |  | Proposal due
2026-10-05 | 112
2026-10-06 | 94
2026-10-07 | 76 |  | Sprint 1 due
2026-10-08 | 57
2026-10-09 | 38
2026-10-10 | 19
2026-10-11 | 0 |  | Sprint 2 + Final Project due

## Release Backlog
Release Backlog – Smart Waste Image Classification and Monitoring System
Priority | Sprint | Feature | Backlog Item | Acceptance / Expected Result | Status
High | Sprint 1 | Dataset | Prepare TrashNet dataset | Six classes inspected, cleaned/preprocessed, and split 70/15/15 | Planned
High | Sprint 1 | AI Model | Implement and train baseline CNN | Baseline six-class model trains and produces evaluation outputs | Planned
High | Sprint 1 | Sprint Evidence | Prepare Sprint 1 code/video/documentation evidence | Required individual and group Sprint 1 artifacts prepared | Planned
High | Sprint 2 | Backend | Integrate FastAPI | API receives image and returns model prediction | Planned
High | Sprint 2 | GUI | Integrate Flet interface | User can provide image and view classification result | Planned
High | Sprint 2 | Model Integration | Verify model/ONNX inference | Inference works in the application environment | Planned
High | Sprint 2 | Testing | Perform final system testing | Core workflow passes functional tests | Planned
High | Sprint 2 | Final Deliverables | Prepare video, documentation, source code, README | All final project deliverables ready for Oct. 11 submission | Planned

## Project Notes
Project Schedule Notes
Project | Smart Waste Image Classification and Monitoring System
Student | Lester Van E. Rivera
Work Mode | Solo / Individual Project
Proposal Deadline | October 4, 2026
Sprint 1 Individual Submission | October 7, 2026
Sprint 1 Group Deliverables | October 7, 2026
Sprint 2 Individual Submission | October 11, 2026
Sprint 2 Group Deliverables | October 11, 2026
Final Project Submission | October 11, 2026
Final Deliverables | Presentation video, project documentation, source code folder with README
Important Course Context | Lab 4 is due Oct. 11 and Lab 5 is due Oct. 14; these are separate course lab deadlines and are not treated as project sprints.
Scope | Single-item six-class waste image classification

## Submission Map
Submission Map
Deliverable | Deadline | What It Contains | Schedule Coverage
Project Proposal | 10/04/2026 | Proposal PDF + project schedule | Sprint 1 planning
Project Sprint 1 – Individual | 10/07/2026 | Individual contribution/evidence | Sprint 1
Project Sprint 1 – Group Deliverables | 10/07/2026 | Proposal, schedule, code/data/evidence artifacts | Sprint 1
Project Sprint 2 – Individual | 10/11/2026 | Individual Sprint 2 contribution/evidence | Sprint 2
Project Sprint 2 – Group Deliverables | 10/11/2026 | Sprint 2 group artifacts | Sprint 2
Project / Final Deliverables | 10/11/2026 | 10–15 min video, documentation, source code + README | Sprint 1 + Sprint 2